TERMS OF REFERENCE

Facilitation and Development of Cannabis Masterplan

1.	BACKGROUND	2

2.	PURPOSE AND OBJECTIVES OF THE MASTERPLAN	3

3.	SCOPE OF THE MASTERPLAN	3

4.	METHODOLOGY	6

5.	QUALIFICATIONS AND EXPERIENCE	6

6.	PROJECT DELIVERABLES	7

7.	PRICE	8

8.	CONTRACTUAL PERIOD	8

9.	CONDITIONS	8

10.	OBLIGATIONS	9

11.	PROPOSAL SUBMISSION AND EVALUATION	11

12.	deadline AND Enquiries	12

# BACKGROUND

1.1	Government approved the Re-invigorated Industrial Strategy (RIS) for South Africa (SA) in June 2019. A cornerstone of the Industrial Strategy is the development of sector-focused Master Plans in 15 priority sectors. One of these sectors is Cannabis. The Master Plan approach has been implemented in the Autos sector over the last decade and has proven to be a highly effective means of creating stakeholder support for a coordinated approach to developing industrial sectors.

1.2	A Master Plan is a comprehensive plan of action developed by Government, Business and Labour which seeks to achieve a common policy objective e.g. protect jobs, create jobs, deepen capabilities in the sector, expand exports, and/or prepare for the impact of possible policy changes. The Master Plan is typically time-bound and incorporates various actions across the 3 main stakeholders, sequenced to achieve maximum socio-economic impact.

1.3	The Economic Research and Coordination unit of Department of Trade, Industry and Competition (the dtic) is inviting qualified and experienced research organisations, policy practitioners and research specialists to submit proposals to facilitate and develop the Cannabis Master Plan.

1.4 	South Africa is contemplating the establishment of the Cannabis industry in order to diversify the economy and to increase economic growth, create jobs and for poverty alleviation. Thus, a decision had been taken to develop the National Cannabis Master Plan that will provide a broad framework for the development and growth of this industry.

1.5	A service provider is required to complement this work by conducting research work into various pillars of this master plan as well as other related matters. The development of the Cannabis master plan is following an integrated approach with various affected sector departments assigned different pillars to lead or to support. The scope of the master plan includes both hemp and dagga, covering the Medicinal use, Cosmetics, Food and Beverages, Industrial use and Recreational use. The research work should also indicate appropriate mechanism for implementation, funding and monitoring.

# PURPOSE AND OBJECTIVES OF THE MASTERPLAN

2.1	The purpose of this undertaking is to conduct comprehensive scoping and research exercise to provide accurate, current, and quantifiable data of the South African Cannabis industry. This would inform the development of appropriate interventions to support the longer-term growth of the industry and be inclusive of existing capacity and structure of the industry, the       regulatory and institutional public and private sector environment, barriers       and constraints as well as market failures and opportunities for the sector.

2.2	The primary objective of the Masterplan process is to develop an agreed-upon set of actions, with timeframes, that all stakeholders in a sector or value-chain commit to implementing for the benefit of the sector or value-chain. The objectives of the masterplan include encouraging sector growth, investment, job creation and competitiveness.

# SCOPE OF THE MASTERPLAN

The scope of this assignment includes the following:

3.1	Comprehensively reviewing the South African Cannabis value-chain’s present position and policies to establish a sound empirical picture of the sector which all stakeholders support. This should include details such as:

  - the sectors’ growth;

  - competitiveness, employment;

  - skills and transformation status;

  - contribution or position in relation to local and/or global industry;

  - relevant sector growth strategies adopted by other countries or sectors.

  - Where existing, current, and relevant research is in place, this could be relied upon.

3.2	Completing a SWOT or similar assessment of the sector based on extensive consultation with industry stakeholders, experts in associated local or international research organisations, and up/downstream value-chain participants. The SWOT must locate the SA industry in a global context and draw lessons from international successes.

3.3	Convene regular, focused stakeholder or reference group meetings/workshops to assess and strengthen the analysis of the sector, and ultimately reach agreement with stakeholders on a joint vision and mission statement for the sector.

3.3	Propose, in consultation with the sector, DRAFT programmes and priorities for time-bound, collective action (by industry, government and labour) to achieve the vision for the sector. It is crucial that stakeholder buy-in and active support for the actions is obtained.

3.4	Develop policy and regulatory recommendations for government, and project proposals to drive the masterplan deliverables

3.5	Develop time-bound development targets for industry sector and labour.

3.6	Propose an appropriate institutional structure/s to drive implementation of the Masterplan, if not suitable or already in place.

3.7	Package the baseline, SWOT analysis and draft Masterplan into a high-quality, narrative report and presentation for use by stakeholders. This will be required by 30th May 2021.

3.8	Identify and deliberate on best global practices in terms of effective regulatory systems of Cannabis industry that will be appropriate for South Africa.

3.9		Identify and describe top global best practices of developing and supporting the growth of a sustainable Cannabis seed industry in this country.

3.10		Describe key focus areas for research and technology development that will be relevant for South Africa in supporting the Cannabis industry.

3.11	Identify and discuss top global best practices that South Africa can adopt in supporting Cannabis producers, especially those that are resource poor.

3.12	Provide analysis of global and domestic markets through:

- Investigating the demand and supply of Cannabis and its products on domestic and foreign markets.

- Identifying niche markets that South Africa Cannabis industry can tap into.

- Identify the main competitors and their strengths and weaknesses.

- Analyzing and recommending market information systems that South Africa can use.

3.13	Identify and discuss best global best practices regarding enterprise and supplier development mechanisms that South Africa can use to develop the Cannabis industry.

3.14	Identify and deliberate on global practices that South Africa can use in developing its capacity in terms of product development and manufacturing regarding the Cannabis industry.

3.15	Discuss and analyse how South Africa can use education and training to      support of the Cannabis industry.

3.16	Describe the role of information and awareness in supporting the       development and growth of the Cannabis industry in this country.

3.17	Determine and describe how the various social partners, namely business, labour, communities and government, should implement their key commitments under various pillars.

3.18	Identify global best practices in terms of implementation, funding and         monitoring the implementation of the master plan.

3.19	Map out the economic development programs that exist from various sector departments and private sector that could be used to support the commercialization of cannabis value chain.

3.20	Provide adaptable recommendations for the development of cannabis industry in South Africa.

# METHODOLOGY

4.1	Although there is a standardised and ‘prescribed’ methodology for the development of Masterplans, service providers must outline detailed, well thought-through and articulated approaches which they will apply to conduct the Masterplan process. The proposed approaches must be outcomes-oriented; explicitly outlining actions and the measures that will be taken to ensure a stakeholder-driven process, stakeholder buy-in and ownership of the Masterplans across all relevant Government, Business and Labour constituencies.

4.2	The above is important because service providers’ proposals will be evaluated on proposed methodology, amongst other criteria.

4.3	The Service Provider is expected to clearly stipulate the approach and provide a step-by-step explanation of the proposed process to reach the end result of this requirement.

4.4	It will be imperative for the Service Provider to outline in the methodology why a particular method was chosen, what pros, cons and risk factors are.

4.5	The use of appropriate research techniques or approaches based on the need to involve and achieve the highest participation rate possible of individual companies/ industry associations into the process.

# QUALIFICATIONS AND EXPERIENCE

Service Providers must propose well-qualified and experienced teams which meet the following minimum requirements:

  - The team leader must have a relevant post graduate qualification in (inter alia) agricultural economics, economics, business Management, development studies, business administration, entrepreneurship, finance, or business management.

  - A minimum of ten (10) years proven track record and experience in the following: research, rural economic development, agriculture and agro-processing, pharmaceutical, cosmetics, industrial development, value chain analysis especially for the cannabis industry and project management skills.  Finally, the team leader must have knowledge and understanding of the socio-economic challenges facing SA, key local stakeholders, and relevant economic and/or industrial policies and programmes implemented in post-Apartheid SA. Specific knowledge of the sector and credibility with sector stakeholders will be an advantage.

  - The other team members must have a degree in the following fields: -agricultural economics or economics, medical / pharmaceutical qualification, project management, development studies, business administration, entrepreneurship, finance, or similar studies.

  - The core team must demonstrate capacity and capabilities in the following: a minimum of 5 years of proven track-record and experience in research, rural economic development, agriculture, and agro-processing, pharmaceutical, cosmetics, industrial development, value chain analysis of cannabis industry. In addition, the core team must possess experience in economic research, negotiations, enterprise development, project management, industrial finance. The core team must also have knowledge of key government economic policies, especially industrial policy and demonstrate ability in stakeholder mobilisation and management.

# PROJECT DELIVERABLES

6.1	Appointed service providers will be expected, with the buy-in of key stakeholders, to submit the following deliverables:

- Short report (10-20 pages) which describes the:

  - Nature of the value-chain,

  - The key companies (value chain players),

  - High-level data covering (inter alia) employment, skills, transformation status, value-addition, investment, exports, imports, productivity metrics, input prices, consumer demand, high-level outlook (including global outlook), competitiveness, areas of strategic advantage and international positioning.

- Short SWOT report covering all the main subsectors or value-chains.

- Draft Masterplan structured as per the template provided by commissioning party/ies (DPRU & the dtic).

The final report should be submitted in the following format:

- Final report (electronic copy) with notes of the methodology used

- Executive summary in word format

- PowerPoint presentation of the report

- Four (4) hard copies of the final report

- Three (3) copies of CD version of the Executive Summary and final report.

# PRICE

7.1	A detailed (itemised) budget quoted in South African currency (ZAR) inclusive of VAT and linked to deliverables must be submitted.

7.2	Hourly rates must be inclusive of all applicable taxes.

# CONTRACTUAL PERIOD

8.1	The entire Masterplan process must be completed within 6 months of commencement. However, service providers must take note of the first deliverables that must be submitted by 30th of May 2021. The commissioning parties are open to reasonable negotiations in this regard.

Format of the report should be in line with areas of focus.

# CONDITIONS

9.1	An appointment/engagement letter will be signed before work commences; followed by a contractual agreement within 4 weeks of appointment. Work will start on the basis of appointed service providers having signed appointment letters, pending signing of contractual agreements.

9.2 	Proposed key staff members must participate actively and be available to perform services in accordance with the service level agreement and the engagement letter. In instances where a proposed key staff member is not available to perform services at a specific period, the appointed service provider will be responsible to provide a replacement with similar qualifications and experience in order to guarantee the same standard of work to the commissioning parties.  Each team member’s role must be clearly outlined in the project plan.

9.3	The commissioning parties reserves the right to vet all qualifications and other documentation provided by the service provider to verify relevant qualifications, experience and expertise prior to the acceptance of the service provider’s appointment.

9.4	The commissioning parties reserve the right to conduct supplier due diligence prior to final award or at any time during the contract period.

9.5	Copyright and intellectual property rights to all documentation, reports etc. that emanate from this assignment will vest with the dtic and the relevant government departments.

9.6	This project and all contracts emanating there from will be subject to the General Conditions of Contract issued in accordance with Treasury Regulation 16A published in terms of the Public Finance Management Act, 1999 (Act 1 of 1999). Special Conditions of Contract are supplementary to that of the General Conditions of Contract. Where the Special Conditions of Contract are in conflict with the General Conditions of Contract, the Special Conditions of Contract prevail.

9.7	The service provider must ensure that their tax matters are in order in line with the Preferential Procurement Policy Framework Act and the Treasury Regulations.

9.8	The award of this project may be subject to price negotiation.

# OBLIGATIONS

10.1	The commissioning parties undertake to

- Appoint a project steering committee which shall be responsible for supervising the project.

- Appoint a Project Leader/s to serve as the contact person/s on all matters relating to the project.

- The project leader will review, evaluate and approve the services provided by consultants or researchers against the Service Level Agreement on an on-going basis.

- Supply all reasonable, relevant, available data and information required and requested by the consultants / researchers for the proper execution of the services, and such assistance as shall reasonably be required by consultants or researchers in carrying out their duties under this contract.

10.2	The appointed service provider undertakes to:

- Act as an independent contractor in respect of the work.

- Attend meetings with the commissioning parties and their representatives whenever required to do so for the purposes of obtaining information or advice with regard to the work and assignments or any matters arising there from or in connection therewith.

- Be responsible for its own computers and its own technical literature to adequately perform its functions.

- Exercise all reasonable skill, care and diligence in the execution of the work and shall carry out their obligations in accordance with international professional standards. The service provider shall in all professional matters act as a faithful advisor to the commissioning agents as well as respecting the laws and customs of the country and provinces in which any business in relation to the project is conducted.

- Have satisfied itself as to the correctness and sufficiency of the rates and prices set out in the contract for the work to be rendered.

- Plan and provide all possible risks that may affect the delivery project on time and what mechanisms are in place to manage such risks.

- Engage meaningfully with the commissioning parties and their representatives throughout the project and ready to assume work as soon as possible.

- Sign a confidentiality declaration when required and keep confidential the contents of the documents and any information availed to them for the purposes of this project. Such information and documents shall remain the intellectual property of relevant commissioning party and their partners.

- Not disseminate any information gathered during the execution of the project, publicize or release media statements in relation to the assignment. Any information gathered during the conduct of the assignment is the property of the relevant commissioning party and may not be distributed without prior approval.

# PROPOSAL SUBMISSION AND EVALUATION

11.1	Proposal must be submitted electronically. Technical and Financial proposals must be submitted separately (not in the same document).

11.2 Received proposals will be evaluated in terms of the two phase process.

11.3.1	First phase – Functional evaluation: Evaluation of technical proposals according to the criteria outlined in the table below. For this phase there is a cut-off score of 60% and only the proposals that score 60% and above will be considered during the second phase of evaluation.

Key scores

| Score | Description |
| --- | --- |
| 0 – Non-compliant | No evidence provided to substantiate compliance |
| 1 – Poor | Unacceptable, does not meet set requirements |
| 2 – Average | Reasonable but not sufficient to fully satisfy the set requirements |
| 3 – Good | Fully complies to the set minimum requirements |
| 4 – Very Good | Above average compliance to the set requirements |
| 5 – Excellent | Meets and exceeds the set requirements |

PHASE 1: FUNCTIONAL EVALUATION

| No. | Criteria | Weight | Rate (0-5) | Total Score |
| --- | --- | --- | --- | --- |
| 1 | Team’s Qualifications & Relevant Experience | 40% |  |  |
| 2 | Proposed methodology | 30% |  |  |
| 3 | Service Provider’s interpretation and understanding of the TORs | 30% |  |  |
|  | TOTAL | 100% |  |  |

11.3.2	Second phase: Price and B-BBEE status level. During the second phase points will be calculated for price and B-BBEE scores in accordance with the amended PPP Regulations pertaining to the Preferential Procurement Policy Framework Act, Act no. 5 of 2000 that came into effect on 7 December 2011.

PHASE 2: PRICE AND B-BBEE PREFERENCE POINTS

|  | 80/20 PRINCIPLE | POINTS |
| --- | --- | --- |
| 1 | Price | 80 |
| 2 | B-BBEE status level of contribution | 20 |
|  | MAXIMUM POINTS | 100 |

# deadline AND Enquiries

  - Proposals must be submitted by email to Mira.Blumbergpahad@uct.ac.za. The deadline for the submission of proposals is Thursday 4th March 2021 no later than 10.00.

  - All submissions should use the email subject line “IGP RFP 07 Cannabis Masterplan”.

    - All technical and bid-related questions should be directed in writing to the following official:

Ms. Kezia Lilenstein

Project Manager: Inclusive Growth Programme

Development policy Research Unit

University of Cape Town

Email: kezia.lilenstein@uct.ac.za